## Sheet1
Week | Task | Description
18-22 (Abril) | Close Converter V01.00 | Ready the converter for n controller bi-directional communication | PS
| Test Converter | Test converter for n controller bi-directional communication | PS
| Close Software Documentation V00 | Requirements, Architecture, Technical, End User, Marketing | PS
| Make a new Test MCR | Second prototype board for new software testing | LS
| Receive MCR | MCR board used in Intertraffic 2016 | APS
| Werner Von Siemens Award | Verify appplication | PS / APS
25-29 (Abril) | MCR Software V01.00 | Update MCR communication protocol and firmware | PS
| Test MCR software | Test MCR board new firmware | PS
| APN Configuration | Contact Vodafone to fix the APN | PS
| Bussiness Model (with Daniel) |  | MR / APS
02-06 (Maio) | New Hardware Design V01.00 | New batteries and component organization | VM
| Test Converter + MCR Software | Test new MCR design with the new firmware | PS
| Hardware Documentation V00 | Components, Limitations, Configuration | PS
09-13 (Maio) | Final Test phase |  | PS
| Technical Review | Requirements for the next version of the board (UI, Configuration, …) | PS / APS
16-20 (Maio) | Start Pilot phase (Porto)