## Sheet1
Week | Task | Description | Responsible | Remarks
18-22 (Abril) | Close Converter V01.00 | Ready the converter for n controller bi-directional communication | PS | Including full functionality between converter and smartGuard
| Test Converter | Test converter for n controller bi-directional communication | PS
| Close Software Documentation V00 | Requirements, Architecture, Technical, End User, Marketing | PS | Revision of document structure on April 20th (jour fixe)
| Make a new Test MCR | Second prototype board for new software testing | LS | With extend inputs for blinking state detection and corrected capacity of batteries
| Receive MCR | MCR board used in Intertraffic 2016 | APS
2016-04-24 | Werner Von Siemens Award | Verify appplication | PS / APS
25-29 (Abril) | MCR Software V01.00 | Update MCR communication protocol and firmware | PS
| Test MCR software | Test MCR board new firmware | PS
| APN Configuration | Contact Vodafone to fix the APN | PS
| Bussiness Model (with Daniel) |  | MR / APS
02-06 (Maio)
2016-05-04 | New Hardware Design V01.00 | New batteries and component organization | VM
2016-05-06 | Case for MCR | Outer case for the new MCR version. | LA / APS
| Test Converter + MCR Software | Test new MCR design with the new firmware | PS
| Hardware Documentation V00 | Components, Limitations, Configuration | PS
2016-05-11 | Handbook for MCR | Technical Details, Instruction Manual, I/O Details, Configuration Manual | LA
09-13 (Maio) | Final Test phase |  | PS
| Technical Review | Requirements for the next version of the board (UI, Configuration, …) | PS / APS
16-20 (Maio) | Start Pilot phase (Porto)
2016-05-18 | Send Demo Kit to Germany | Ready and send the Demo Kit for the ITS Service Summit | PS